## Sheet1
Step # | Depends On Step # | Task |  | Assigned To | Target Date | Date Completed
1 |  | PLANNING
Meet with leadership team to establish goals, responsibilities and schedule
Determine best sources of data for membership, advancement, participation, leadership, training & account balances
Decide whether the site will accept credit card payments and, if so, who will pay the credit card fees
Decide whether to allow adults to request expense reimbursements through the website
Fill out this checklist and send to all leaders
2 | 1 | INITIAL ROSTER
Set up Membership Types
A) If a data source exists, upload membership data for all members
B) Otherwise, enter membership data for leaders who will be helping set up the site
3 | 2 | SECURITY
Assign User Roles to leaders, giving them access to the functions they will need
Send user IDs and passwords to leaders who are helping set up the site
4 | 3 | ROSTER
If not possible to upload membership data, manually enter membership records for everyone
Scouting Units: set age level for all youth members
Set up Committees and their members
Set up Leadership Positions and assign to current leaders
Upload or enter leadership training
Create dynamic subgroups
Ask all leaders to enter their "About Me" section and upload a photo under My Contact Information
5 | 3 | PUBLIC PAGES
Review and update Site Appearance options
Create banner image (optional)
Edit the Home page and About Us pages
Create additional custom pages as needed
Create announcements
Upload forms and documents
Create links to other sites on the Web Links page
6 | 3 | CALENDAR
Review and revise Event Types
Enter event locations
Enter past events for which you plan to upload photos or enter monetary transactions
Enter upcoming events. Use the "copy event" functions to set up meetings and other recurring events
Cub Scouts ONLY: Train leaders to use mobile app to take attendance at events.
7 | 6 | PHOTO GALLERY / VIDEO GALLERY
Upload photos from past events
Upload videos to YouTube and create links from Video Gallery
8 | 4 | ADVANCEMENT (Cub Scouts ONLY)
Upload advancement data from Scoutbook
Train leaders how to sign off on requirements on the website and the app
9 | 3 | INVENTORY/LIBRARY
Enter all library materials into inventory
Enter all shared equipment into inventory
Check out items to members who currently have them
Cub Scouts ONLY: Train leaders to use mobile app to check out and return library materials and troop equipment
10 | 4 | ACCOUNTING
Set up group checking account and enter starting balance
A) If data source is available, upload member balances
B) Otherwise, enter starting balances for each troop member
Set up credit card interface using Square or PayPal
Review and update expense reimbursement settings
Train leaders to use website to request expense reimbursements
Begin monthly statement reconciliation process
11 | 4 | FUNDRAISERS
Set up next fundraiser, including merchandise and sales prizes
Train members how to enter orders and sell on-line via ScoutSales.org
Train fundraising leaders how to use Booth Sales to run in-person fundraiser events
12 | 4 | ROLL OUT
Send user ID's and passwords to all members
Demonstrate/discuss new website at group meeting
Cub Scouts ONLY: Train scouts and parents to use mobile app to sign up for events and give permission
Set up automated electronic newsletter
Plan on-going site operation at leadership meeting